## Sheet1
Procuring Entity Name | MINISTRY OF BASIC EDUCATION
Procurement Plan for year | 2022
Date Created | 2022-01-07
Comments
Estimated dates
Category | Description | UNSPSC | Ref No | Envisaged Quantity | Unit | Estimated Budget | BUDGET CODE | Source of Funds | Prequalification (Y/N) | Procurement Method | Advert Publication Date | Award Date | Project Start Date | Project Completion Date | PROCUREMENT METHOD RATIONALE
Works | Rehabilitation / Renovation of Special Education Centre Umuchu |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23020107/05000004 | ANSG | N | Selective | 2022-04-04 | 28/04/2022 | 2022-01-05 | 14/06/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Rehabilitation of dilapilated building at Basden Memorial Education Centre Isulo |  | MOBE/PRSD/AK/385/1 | 5 |  | 5000000 | 17001001/23020107/05000004 | ANSG | N | Selective | 2022-04-04 | 28/04/2022 | 2022-01-05 | 14/06/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Supply | Procurement of Consumables for production Units of 10 GTCs |  | MOBE/PRSD/AK/385/1 |  |  | 10000000 | 17001001/23020107/05000008 |  |  | Selective | 2022-04-04 | 28/04/2022 | 2022-01-05 | 14/06/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Rehabilitation / Renovation of Special Education Centre Odoakpu |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23020107/05000004 | ANSG | N | Selective | 1900-01-05 | 28/04/2022 | 2022-01-05 | 14/06/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Conduct of 2020/2021 Annual School Census |  | 58 |  | NGN | 7015000 | 17001001/23020118/05000013 | ANSG | N | direct | 2022-04-04 | 28/04/2022 | 2022-01-05 | 14/06/2022 | Effectiveness of the procurement process
Supply | Supply of Stationeries to EDC |  | MOBE/PRSD/AK/385/1 |  | NGN | 4000000 | 17001001/23010124/05000010 | ANSG | N | direct | 2022-04-04 | 28/04/2022 | 2022-01-05 | 14/06/2022 | Effectiveness of the procurement process
Services | a) international literacy day celebration involving the 21 LGAs and 286 learning Centers |  | MOBE/PRSD/AK/385/1 |  | NGN | 2500000 | 17001001/23020107/05000003 | ANSG | N | Direct | 2022-01-08 | 22/08/2022 | 24/08/2022 | 21/09/2022 | Effectiveness of the procurement process
Supply | Establishment of one model vocational education Centre in one of the 3 senatorial zones in the state |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 4000000 | 17001001/23020107/05000003 | ANSG | N | Selective | 2022-01-08 | 22/08/2022 | 24/08/2022 | 21/09/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Advocacy, sensitazation,mobilazation ,monitoringin the 21 LGA |  | MOBE/PRSD/AK/385/1 |  | NGN | 1000000 | 17001001/23020107/05000003 | ANSG | N | Direct | 2022-01-08 | 22/08/2022 | 24/08/2022 | 21/09/2022 | Effectiveness of the procurement process
Works | Changing of ANNFE louvers windows to Aluminum window |  | MOBE/PRSD/AK/385/1 |  | NGN | 500000 | 17001001/23020107/05000003 | ANSG | N | Direct | 2022-01-08 | 22/08/2022 | 24/08/2022 | 21/09/2022 | Effectiveness of the procurement process
Services | Training of 798 facilitators on androgogical scales in six(6) Edu zones of the state |  | MOBE/PRSD/AK/385/1 | 798 | NGN | 2000000 | 17001001/23020107/05000003 | ANSG | N | Selective | 2022-01-08 | 22/08/2022 | 24/08/2022 | 21/09/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Rehabilitation / Renovation of Basden Mem Special Edu Centre, Isulo |  | MOBE/PRSD/AK/385/1 |  | NGN | 10000000 | 17001001/23020107/05000004 | ANSG | N | Open | 2022-01-08 | 22/08/2022 | 24/08/2022 | 21/09/2022 | Accountability and Transparency
Supply | Procurement of laptop Computers and instructional materials for Basden Mem Special Centre,Isulo |  | MOBE/PRSD/AK/4 | 3 | NGN | 1000000 | 17001001/23020107/05000004 | ANSG | N | Direct | 2022-01-08 | 22/08/2022 | 24/08/2022 | 21/09/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Rehabilitation of existing buildings/construction of additional classrooms and dormitories in 7 locations in Anambra south Senatorial Zone |  | MOBE/PRSD/AK/385/1 |  | NGN | 4666666.666 | 17001001/23020107/05000005 | ANSG | N | Open | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Accountability and Transparency
Works | Rehabilitation of existing buildings/construction of additional classrooms and dormitories in 7 locations in Anambra East Senatorial Zone |  | MOBE/PRSD/AK/385/1 |  | NGN | 4666666.666 | 17001001/23020107/05000005 | ANSG | N | Open | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Rehabilitation of existing buildings/construction of additional classrooms and dormitories in 7 locations in Anambra Central Senatorial Zone |  | MOBE/PRSD/AK/385/1 |  | NGN | 4666666.666 | 17001001/23020107/05000005 | ANSG | N | Open | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Accountability and Transparency
Supply | Supply of teaching textbooks/handbook, Manuals/teaching ,charts,slides and instructional materials |  | MOBE/PRSD/AK/385/1 |  | NGN | 4000000 | 17001001/23010124/05000006 | ANSG | N | Direct | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Effectiveness of the procurement process
Supply | Installation of internet/ ICT facilities in Primary & Sec. Schools {Local, Zonal & National} |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23010124/05000007 | ANSG | N | Selective | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Timely delivery of the project & cost effectiveness of the procurement process
Services | On-line Registration and internet services |  | MOBE/PRSD/AK/385/1 |  | NGN | 9000000 | 17001001/23010124/05000007 | ANSG | N | Direct | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Effectiveness of the procurement process
Services | Screening, verification and co-ordination officers |  | MOBE/PRSD/AK/385/1 |  | NGN | 2000000 | 17001001/23010124/05000007 | ANSG | N | Direct | 2022-10-25 | 2022-11-12 | 2022-11-16 | 2022-11-19 | Effectiveness of the procurement process
Works | Rehabilitation and renovation of 6 classrooms and workshops block each at 4 GTCs |  | MOBE/PRSD/AK/385/1 |  | NGN | 148000000 | 17001001/23010124/05000008 | ANSG | N | Open | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Accountability and Transparency
Supply | Procurement of equipment/local materials and construction work |  | MOBE/PRSD/AK/385/1 |  | NGN | 260000000 | 17001001/23010124/05000008 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Hosting of NBTE staff for accreditation for 7 days and payment for accreditation 0f 16 trade course |  | MOBE/PRSD/AK/385/1 |  | NGN | 11000000 | 17001001/23010124/05000008 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Cost of consumables for production units at 12 GTCs |  | MOBE/PRSD/AK/385/1 |  | NGN | 12000000 | 17001001/23010124/05000008 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Development of Stem Projects for national and international exposition and stem fair working shop |  | MOBE/PRSD/AK/385/1 |  | NGN | 16000000 | 17001001/23010124/05000009 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Supply | Provision of textbooks/handbooks, instructional materials and guides to teachers |  | MOBE/PRSD/AK/4 |  | NGN | 1000000 | 17001001/23010124/05000009 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Promotion of boy/girl child education using role models, career days, children re-orientation programmes. |  | MOBE/PRSD/AK/385/1 |  | NGN | 4000000 | 17001001/23010124/05000009 | ANSG | N | direct | 2022-09-13 | 2022-09-24 | 2022-10-18 | 2022-10-21 | Timely delivery of the project & cost effectiveness of the procurement process
Supply | Purchase of (i) 2 nos photocopier machine (ii) 7 nos Printers (iii) 5 nos laptops |  | MOBE/PRSD/AK/385/1 |  | NGN | 1800000 | 17001001/23010124/05000010 | ANSG | N | direct | 2002-01-18 | 2022-01-25 | 2022-02-18 | 2022-02-21 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Renovation (re-roofing of flash points, wall fixing, landscaping, fence upgrading, fortification of back doors and windows with metals/iron etc) at CERC |  | MOBE/PRSD/AK/385/1 |  | NGN | 2000000 | 17001001/23010124/05000012 | ANSG | N | Selective | 2022-04-04 | 28/04/2022 | 2022-01-05 | 14/06/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Extra Air Conditioners for CBT halls, reconstruction of CBT tables & chairs and its re-networking at CERC |  | MOBE/PRSD/AK/385/1 |  | NGN | 1800000 | 17001001/23010124/05000012 | ANSG | N | Open | 2022-08-18 | 2022-08-22 | 2022-09-18 | 2022-09-22 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Beautification and Upgrading of Nursery and Pre-nursery Units and Staff training on Entrepreneurial Education at CERC |  | MOBE/PRSD/AK/385/1 |  | NGN | 3000000 | 17001001/23010124/05000012 | ANSG | N | Open | 2022-08-18 | 2022-08-22 | 2022-09-18 | 2022-09-22 | Timely delivery of the project & cost effectiveness of the procurement process
Supply | Purchase of two(2) overhead water tank, new water pumping machine and water pipes at CERC |  | MOBE/PRSD/AK/385/1 | 2 | NGN | 1200000 | 17001001/23010124/05000012 | ANSG | N | Open | 2022-08-18 | 2022-08-22 | 2022-09-18 | 2022-09-22 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Conduct of School Mapping of all public schools |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23010124/05000013 | ANSG | N | Open | 2022-08-18 | 2022-08-22 | 2022-09-18 | 2022-09-22 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Preparation of Education digest, Periodic Publication on Strides in Education sector |  | MOBE/PRSD/AK/385/1 |  | NGN | 4000000 | 17001001/23010124/05000013 | ANSG | N | direct | 2002-01-18 | 2022-01-25 | 2022-02-18 | 2022-02-21 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Monitoring and Evaluation of various projects and Monitoring of learning Achievements in Schools |  | MOBE/PRSD/AK/385/1 |  | NGN | 7000000 | 17001001/23010124/05000013 | ANSG | N | direct | 2002-01-18 | 2022-01-25 | 2022-02-18 | 2022-02-21 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Development/Review of State Education Operational Plan (SESOP) and Education Sector Plan including printing- |  | MOBE/PRSD/AK/385/1 |  | NGN | 3500000 | 17001001/23010124/05000013 | ANSG | N | direct | 2002-01-18 | 2022-01-25 | 2022-02-18 | 2022-02-21 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Capacity building for EMIS staff |  | MOBE/PRSD/AK/385/1 |  | NGN | 3000000 | 17001001/23010124/05000013 | ANSG | N | direct | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Supply | Procurement of projector and screen |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 350000 | 17001001/23010124/05000013 | ANSG | N | direct | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
| Purchase of new office equipment and repair of damaged ones at the ministry |  | MOBE/PRSD/AK/4 |  | NGN | 2000000 | 17001001/23010124/05000014 | ANSG | N | direct | 2022-08-04 | 2022-08-06 | 2022-08-18 | 2022-08-21 | Timely delivery of the project & cost effectiveness of the procurement process
Services | capacity building for ZEOs and AEOs |  | MOBE/PRSD/AK/385/1 |  | NGN | 3000000 | 17001001/23010124/05000014 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 2022-05-29 | Timely delivery of the project & cost effectiveness of the procurement process
Services | . Award of Scholarship to indigent & special needs pupils and students in primary and secondary schools, intelligent pupils and students, orphans and vulnerable children. |  | MOBE/PRSD/AK/385/1 |  | NGN | 14000000 | 17001001/23010124/05000016 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Redemption of ongoing Scholarship commitment |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23010124/05000016 | ANSG | N | direct | 2022-10-25 | 2022-11-12 | 2022-11-16 | 2022-11-19 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Preparation of Education digest, Periodic Publication on Strides in Education sector |  | MOBE/PRSD/AK/385/1 |  | NGN | 2000000 | 17001001/23010124/05000017 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Sensitization/ mobilization of Education Stakeholders/Schools on adoption and application of QA instruments to improve standards/ enhance teachers’ quality |  | MOBE/PRSD/AK/385/1 |  | NGN | 1000000 | 17001001/23010124/05000018 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Training of Peer Educator, Teachers and other relevant personnel & Formation of Anti-AIDS clubs in schools and Monitoring and Evaluation of HIV/AIDS Projects . |  | MOBE/PRSD/AK/385/1 |  | NGN | 2000000 | 17001001/23010124/05000019 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 2022-05-29 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Hosting of school coordinators, Advisory /Advocacy committee, & Project Implementation Team meetings |  | MOBE/PRSD/AK/385/1 |  | NGN | 1000000 | 17001001/23010124/05000019 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Demolition and erection of three-storey classroom block at Metu Memorial Secondary school, Onitsha and Construction of 14 Science laboratories in 14 selected schools. |  | MOBE/PRSD/AK/385/1 |  | NGN | 90000000 | 17001001/23010124/05000022 | ANSG | N | Open | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Supply | Procurement of (i) 7 nos Digital photo Cameras for 6 education zones and Headquarter,(ii) 7 nos Projector and screen for 6 education zones and Headqurters |  | MOBE/PRSD/AK/385/1 |  | NGN | 1050000 | 17001001/23010124/05000022 | ANSG | N | Open | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Training of 480 Maths/Physics Teachers on use of GPS and training of 262 principals on Census |  | MOBE/PRSD/AK/385/1 |  | NGN | 10496000 | 17001001/23010124/05000022 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 2022-05-29 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Monitoring and Supervision of 2021/2022 School Census |  | MOBE/PRSD/AK/385/1 |  |  | 3000000 | 17001001/23010124/05000022 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Conduct of exams and Printing of Question Papers |  | MOBE/PRSD/AK/385/1 |  | NGN | 1435800 | 17001001/23010124/05000022 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Works | Construction of proper flood channels for schools in flood prone areas |  | MOBE/PRSD/AK/4 |  | NGN | 5000000 | 17001001/23010124/05000022 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Supply | Procurement of Water Sumo and water tank for PPSSC Headquarters |  | MOBE/PRSD/AK/385/1 |  | NGN | 175000 | 17001001/23010124/05000022 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
supply | Purchase of 7 nos photocopier machine for the 6 departments and the Chairman's office at Headquarters and 7 nos Printers for the 6 departments and Chairman's office at Headquarters. |  | MOBE/PRSD/AK/385/1 |  | NGN | 826000 | 17001001/23010124/05000022 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Capacity building /training /retraining of French teachers in non-pilot schools and providing support for the activities of Nigerian Association of French Teachers (NAFT) |  | MOBE/PRSD/AK/385/1 |  | NGN | 3000000 | 17001001/23010124/05000024 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Sports festivals- Sports competitions for primary and secondary at LGA/Six educational zones, state and national levels, shell cup football for boys only,Nestle milo basketball competition,Airtel football competition all for secondary schools at LGA,state,regional and national levels. |  | MOBE/PRSD/AK/385/1 |  | NGN | 9000000 | 17001001/23010124/05000025 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Training / re-organization of physical and health education instructors and games teachers in primary schools. |  | MOBE/PRSD/AK/385/1 |  | NGN | 4000000 | 17001001/23010124/05000025 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Sponsorship of physical and health education specialist teacher’s/sports teachers to national conferences/seminars /workshops and hosting of state school sports Federation meetings for physical education teachers, games masters etc |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23010124/05000025 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Sponsorship of national school sports federation meetings |  | MOBE/PRSD/AK/385/1 |  | NGN | 1000000 | 17001001/23010124/05000025 | ANSG | N | direct | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Sponsorship of Special Sports for the handicapped school children and Sponsorship of International school sports competitions involving football, volleyball Handball, Basketball, Hockey, Athletics, |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23010124/05000025 | ANSG | N | direct | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Sponsorship of Principals cup secondary school’s sports competition and Sponsorship of state Governor’s cup sports competition for primary and secondary schools |  | MOBE/PRSD/AK/385/1 |  | NGN | 4000000 | 17001001/23010124/05000025 | ANSG | N | direct | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Governors secondary school football competition |  | MOBE/PRSD/AK/385/1 |  | NGN | 2000000 | 17001001/23010124/05000025 | ANSG | N | direct | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Organize two-day workshops for 5,000 teachers on emergency preparedness |  | MOBE/PRSD/AK/385/1 | 5000 | NGN | 2000000 | 17001001/23010124/05000026 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Capacity building/training, Seminars/Conferences: local, National & International for 500 staff of MoBE |  | MOBE/PRSD/AK/385/1 | 500 | NGN | 2000000 | 17001001/23010124/05000026 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Organize 5-day workshop on effective teaching and learning skills for 1500 teachers |  | MOBE/PRSD/AK/4 | 1500 | NGN | 4000000 | 17001001/23010124/05000026 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
Services | Reading competitions and workshops/seminars/conferences/meetings |  | MOBE/PRSD/AK/385/1 |  | NGN | 2000000 | 17001001/23010124/05000026 |  | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
services | Monitoring, investigation, inspection of libraries, sporting equipment and other facilities in primary and secondary schools& special Education Centres |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23010124/05000030 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
services | Hygiene Promotion/ Communication Programme in Schools |  | MOBE/PRSD/AK/385/1 |  | NGN | 5000000 | 17001001/23010124/05000033 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
services | Capacity building of Igbo teachers and Seminars for the promotion of Igbo language (Subakwa Igbo) |  | MOBE/PRSD/AK/385/1 |  | NGN | 2000000 | 17001001/23010124/05000036 | ANSG | N | direct | 2022-09-13 | 2022-09-24 | 2022-10-18 | 2022-10-21 | Timely delivery of the project & cost effectiveness of the procurement process
services | Sensitization & advocacy for Igbo language promotion and Igbo desk officer-schools cultural festival |  | MOBE/PRSD/AK/385/1 |  | NGN | 3000000 | 17001001/23010124/05000036 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
services | Setting up of Artificial Intelligence (AI), Coding and Robotics Laboratories in 261 Secondary schools |  | MOBE/PRSD/AK/385/1 | 261 | NGN | 5000000 | 17001001/23010124/05000037 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
works | Establishment of 3 Market schools @ Onitsha, Awka and Nnewi |  | MOBE/PRSD/AK/385/1 | 3 | NGN | 12000000 | 17001001/23010124/05000038 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 2022-05-29 | Timely delivery of the project & cost effectiveness of the procurement process
services | Training of 1000 teachers, on professional teacher development skills |  | MOBE/PRSD/AK/385/1 | 1000 | NGN | 4000000 | 17001001/23010124/05000038 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
services | Training of 30 education officers on ICT |  | MOBE/PRSD/AK/385/1 | 30 | NGN | 4000000 | 17001001/23010124/05000038 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 2022-05-29 | Timely delivery of the project & cost effectiveness of the procurement process
| WORLD BANK ASSISTED STATE EDUCATION PROG. & INVEST(SEPIP) |  | MOBE/PRSD/AK/385/1 |  | NGN | 600000000 | 17001001/23010124/05000039 | ANSG | N | direct | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
services | UNIDO-Assisted Entrepreneurship Education for Senior Secondary Schools; justification:To facilitate the strategic effort of Nigeria in developing and introducing entrepreneurship curriculum in 34 skills into the Senior Secondary Schools. |  | MOBE/PRSD/AK/385/1 |  | NGN | 20000000 | 17001001/23010124/05000040 | ANSG | N | direct | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
works | DEVELOPMENT OF MINI STADIUM IN SCHOOLS |  | MOBE/PRSD/AK/385/1 |  | NGN | 200000000 | 17001001/23010124/05000042 | ANSG | N | Open | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF MODEL SECONDARY SCHOOL AT OROMA ETITI |  | MOBE/PRSD/AK/4 |  | NGN | 100000000 | 17001001/23010124/05000043 | ANSG | N | Open | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF MODEL SEC SCHL AT OGBUNIKE |  | MOBE/PRSD/AK/385/1 |  | NGN | 100000000 | 17001001/23010124/05000044 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
works | REHABILITATION OF CSS NNOBI |  | MOBE/PRSD/AK/385/1 |  | NGN | 28000000 | 17001001/23010124/05000045 | ANSG | N | Open | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
works | RENOVATION OF 2 NO CLASSROOM BLOCK AT AGULU GRAMMER SCHL AGULU |  | MOBE/PRSD/AK/385/1 | 2 | NGN | 15000000 | 17001001/23010124/05000046 | ANSG | N | Open | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF MODEL SECONDARY SCHOOL AT ISU VILLAGE, OBA IDEMILI SOUTH |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 85000000 | 17001001/23010124/05000047 | ANSG | N | Open | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF TEACHERS QUARTERS AT ANAMBRA WEST LGA HQ |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000048 | ANSG | N | Open | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF TEACHERS QUARTERS AT OGBARU LGA HQ |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000049 | ANSG | N | Open | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF TEACHERS QUARTERS AT AYAMELU LGA HQ |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000050 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF TEACHERS QUARTERS AT ANAMBRA EAST LGA HQ |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000051 | ANSG | N | Open | 2022-05-05 | 2022-06-30 | 2022-07-15 | 2022-07-18 | Timely delivery of the project & cost effectiveness of the procurement process
works | RENOVATION OF 1 CLASSROOM BLOCK AT IDE GIRL'S SEC.SCH, ENUGU-UKWU |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 15000000 | 17001001/23010124/05000052 | ANSG | N | Open | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Timely delivery of the project & cost effectiveness of the procurement process
works | RENOVATION OF 1 NO 6-ROOM CLASSROOM BLOCK AT OKUTALUKWE SECONDARY SCHOOL ENUGU-UKWU. |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 15000000 | 17001001/23010124/05000053 | ANSG | N | Open | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF MODEL SECONDARY SCHOOL AT IGWEBUIKE GRAMMAR SCHOOL, AWKA |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000054 | ANSG | N | Open | 2022-09-05 | 2022-09-20 | 2022-09-21 | 2022-10-03 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF MODEL SECONDARY SCHOOL AT COMMUNITY SECONDARY SCHOOL, IHITE |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000055 | ANSG | N | Open | 2022-10-25 | 2022-11-12 | 2022-11-16 | 2022-11-19 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF MODEL SECONDARY SCHOOL AT JUSTICE CHINWUBA SECONDARY SCHOOL, AGULERI |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000056 | ANSG | N | Open | 2022-01-04 | 22/04/2022 | 25/04/2022 | 29/5/2022 | Timely delivery of the project & cost effectiveness of the procurement process
works | CONSTRUCTION OF 1 NO MODEL FABRICATION LABORATORY AT ONITSHA |  | MOBE/PRSD/AK/385/1 | 1 | NGN | 100000000 | 17001001/23010124/05000057 | ANSG | N | Open | 2022-05-05 | 2022-08-06 | 2022-08-22 | 2022-08-25 | Timely delivery of the project & cost effectiveness of the procurement process
Services | ANAMBRA STATE MINISTRY OF BASIC EDUCATION ANTI-CORRUPTION STRATEGY |  | MOBE/PRSD/AK/385/1 |  | NGN | 3000000 |  | ANSG | N | Open | 2022-10-25 | 2022-11-12 | 2022-11-16 | 2022-11-19 | Timely delivery of the project & cost effectiveness of the procurement process